## Timing
Project: Client-Website
Duration: "
TIME SCHEDULE
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-03-12 10:00 | 2018-03-13 10:00 | 2018-03-14 10:00 | 2018-03-15 10:00 | 2018-03-16 10:00 | 2018-03-17 10:00 | 2018-03-18 10:00
Begin Client Worksite
Client Questionnaire and goals | Comparative Analysis | Technical Specifications |  | Create Timeline | Create Timeline | Create Timeline
User Scenarios |  | Create Project Proposal | Create Project Proposal | Create Project Proposal
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-03-19 10:00 | 2018-03-20 10:00 | 2018-03-21 10:00 | 2018-03-22 10:00 | 2018-03-23 09:00 | 2018-03-24 09:00 | 2018-03-25 09:00
|  |  |  | Pre Production finished |  | PUBLIC HOLIDAY
Create Timeline | Create Content Chart | Create Content Chart | Create Content Chart | Create Site Map
Create Task List | Create Task List |  | Define Communications
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-03-26 09:00 | 2018-03-27 09:00 | 2018-03-28 09:00 | 2018-03-29 09:00 | 2018-03-30 09:00 | 2018-03-31 09:00 | 2018-04-01 09:00
Design Comps | Design Comps | Client review and selection of Design | Client review and selection of Design | Building Pages | Building Pages | Building Pages
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-04-02 09:00 | 2018-04-03 09:00 | 2018-04-04 09:00 | 2018-04-05 09:00 | 2018-04-06 09:00 | 2018-04-07 09:00 | 2018-04-08 09:00
PUBLIC HOLIDAY
Building Pages | Building Pages | Building Pages | Building Pages | Client Review | Client Review | Client Review
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-04-09 09:00 | 2018-04-10 09:00 | 2018-04-11 09:00 | 2018-04-12 09:00 | 2018-04-13 09:00 | 2018-04-14 09:00 | 2018-04-15 09:00
PUBLIC HOLIDAY
Client Review | Client Review | Final Site Production | Final Site Production | Usability Testing
|  |  | Beta Testing | Beta Testing
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-04-16 09:00 | 2018-04-17 09:00 | 2018-04-18 09:00 | 2018-04-19 09:00 | 2018-04-20 09:00 | 2018-04-21 09:00 | 2018-04-22 09:00
Create Style Guide | Browser testing | Browser testing | Fix bugs | Fix bugs | Fix bugs | Fix bugs
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-04-23 09:00 | 2018-04-24 09:00 | 2018-04-25 09:00 | 2018-04-26 09:00 | 2018-04-27 09:00 | 2018-04-28 09:00 | 2018-04-29 09:00
Production finished |  | Post Production finished
Fix bugs | Define Maintenance Schedule | Project Retrospective
Final presentations